## Sheet2
Task | Duration | Owner | Status | Start date | End date | Dependencies | Milestone
Project Initiantion & Requirement Gathering | 5 | Muhammad Farouk | In progress | 2025-11-04 | 2025-11-08 | - | ✅
Data Collection & Sourcing | 7 | Muhammad Farouk | In progress | 2025-11-11 | 2025-11-19 | 1
Backend & Database Development | 10 | Muhammad Aiman | Not started | 2025-12-20 | 2025-12-03 | 2
AI Model Development (OCR & NLP) | 10 | Tee Kai En | Not started | 2025-12-04 | 2025-12-17 | 3
AI Model Development (Matching Algorithm) | 8 | Tee Kai En, Muhammad Aiman | Not started | 2025-12-18 | 2025-12-29 | 4
Frontend & Dashboard Development | 12 | Muhammad Aiman | Not started | 2026-01-02 | 2026-01-19 | 5
System Integration | 7 | Muhammad Aiman | Not started | 2026-01-22 | 2026-01-30 | 6
Testing & Validation | 8 | Tee Kai En | Not started | 2026-01-31 | 2026-02-11 | 7
Deployment & Documentation | 5 | Tee Kai En | Not started | 2026-02-12 | 2026-02-18 | 8
Final Report & Presentation | 7 | Muhammad Farouk | Not started | 2025-02-19 | 2026-02-27 | 9