## Week 03
Task | Duration | Owner | Status | Start date | End date | Dependencies | Estimated Cost (RM) | Milestone | Deliverable | Notes
Project Initiantion & Requirement Gathering | 5 | Muhammad Farouk | In progress | 2025-10-06 | 2025-11-03 | - | 1240 | ✅
Data Collection & Sourcing | 7 | Muhammad Farouk, Tee Kai En | In progress | 2025-10-13 | 2025-11-24 | 1 | 420
Backend & Database Development | 10 | Muhammad Aiman | Not started | 2025-11-24 | 2026-01-26 | 2 | 1295
AI Model Development (OCR & NLP) | 10 | Tee Kai En | Not started | 2025-11-24 | 2026-01-26 | 3 | 1080
AI Model Development (Matching Algorithm) | 8 | Tee Kai En, Muhammad Aiman | Not started | 2025-12-15 | 2026-02-02 | 4 | 1050
Frontend & Dashboard Development | 12 | Muhammad Aiman, Muhammad Farouk | Not started | 2025-11-17 | 2026-02-02 | 5 | 1505
System Integration | 7 | Muhammad Aiman | Not started | 2026-02-02 | 2026-02-09 | 6 | 805
Testing & Validation | 8 | Tee Kai En | Not started | 2026-02-09 | 2026-02-16 | 7 | 480
Deployment & Documentation | 1 | Tee Kai En | Not started | 2026-02-12 | 2026-02-19 | 8 | 280
Final Report & Presentation | 1 | Muhammad Farouk | Not started | 2026-02-12 | 2026-02-19 | 9 | 480
TOTAL | [6 empty] | 4950

## Week 04 – WBS Tasks
Week 04 – Work Breakdown Structure (WBS): Job Match-Making System
Major Phase | WBS ID | Subtask | Deliverable | Owner | Start | End
Project Initiation & Requirement Gathering | 1.1 | Conduct project meeting & define objectives | Meeting Notes | Muhammad Farouk | 6 Oct 2025 | 10 Oct 2025
| 1.2 | Gather user & store requirements | Requirement List | Muhammad Farouk | 11 Oct 2025 | 20 Oct 2025
| 1.3 | Prepare system scope & approval | Approved Project Scope | Muhammad Farouk | 21 Oct 2025 | 3 Nov 2025
Data Collection & Sourcing | 2.1 | Identify data sources | Data Source List | Muhammad Farouk | 13 Oct 2025 | 20 Oct 2025
| 2.2 | Collect and clean data | Cleaned Dataset | Tee Kai En | 21 Oct 2025 | 10 Nov 2025
| 2.3 | Upload and verify dataset | Verified Data Files | Team | 11 Nov 2025 | 24 Nov 2025
Backend & Database Development | 3.1 | Design database ERD | ER Diagram | Muhammad Aiman | 24 Nov 2025 | 30 Nov 2025
| 3.2 | Create database tables and relationships | Database Schema | Muhammad Aiman | 1 Dec 2025 | 20 Dec 2025
| 3.3 | Develop backend functions (CRUD operations) | Backend Code | Muhammad Aiman | 21 Dec 2025 | 26 Jan 2026
AI Model Development (OCR & NLP) | 4.1 | Collect training samples | Raw Training Data | Tee Kai En | 24 Nov 2025 | 10 Dec 2025
| 4.2 | Train OCR/NLP model | Trained Model | Tee Kai En | 11 Dec 2025 | 15 Jan 2026
| 4.3 | Evaluate and refine model performance | Model Report | Tee Kai En | 16 Jan 2026 | 26 Jan 2026
AI Model Development (Matching Algorithm) | 5.1 | Design matching algorithm logic | Algorithm Design | Tee Kai En | 15 Dec 2025 | 31 Dec 2025
| 5.2 | Implement algorithm into system | Code Implementation | Muhammad Aiman | 1 Jan 2026 | 20 Jan 2026
| 5.3 | Test matching accuracy | Test Report | Team | 21 Jan 2026 | 2 Feb 2026
Frontend & Dashboard Development | 6.1 | Design dashboard UI | UI Mockup | Muhammad Farouk | 17 Nov 2025 | 10 Dec 2025
| 6.2 | Develop frontend components | HTML/CSS/JS Interface | Muhammad Aiman | 11 Dec 2025 | 20 Jan 2026
| 6.3 | Integrate with backend and AI model | Functional Dashboard | Team | 21 Jan 2026 | 2 Feb 2026
System Integration | 7.1 | Integrate all modules | Integrated Build | Muhammad Aiman | 2 Feb 2026 | 5 Feb 2026
| 7.2 | Run system-level testing | Integration Report | Team | 6 Feb 2026 | 9 Feb 2026
Testing & Validation | 8.1 | Perform functional testing | Functional Test Results | Tee Kai En | 9 Feb 2026 | 12 Feb 2026
| 8.2 | Conduct user acceptance test | UAT Report | Team | 13 Feb 2026 | 16 Feb 2026
Deployment & Documentation | 9.1 | Deploy system to production | Live System | Tee Kai En | 12 Feb 2026 | 15 Feb 2026
| 9.2 | Prepare user manual and documentation | User Guide | Tee Kai En | 16 Feb 2026 | 19 Feb 2026
Final Report & Presentation | 10.1 | Compile final project report | Final Report | Muhammad Farouk | 12 Feb 2026 | 17 Feb 2026
| 10.2 | Prepare PowerPoint presentation | Slide Deck | Muhammad Farouk | 18 Feb 2026 | 19 Feb 2026

## Week 05 – Cost & Resources
AI Project Management – Week 05 Report ¦ Budget RM 4,950
WBS ID | Task Name | Resource Type | Resource Name | Hours | Rate (RM/hr) | Total Cost (RM) | Cost Category | Budget Summary
1.1 | Conduct project meetings | Human | Project Lead | 10 | 40 | 400 | Human Resources | Cost Category | Subtotal (RM) | Percentage
1.2 | Gather requirements | Human | Project Lead | 15 | 40 | 600 | Human Resources | Human Resources | 4550 | 91.9%
1.3 | Prepare system scope | Human | Project Lead | 6 | 40 | 240 | Human Resources | Hardware / Cloud | 200 | 4.0%
2.1 | Identify data sources | Human | Data Researcher | 8 | 30 | 240 | Human Resources | Software / Licenses | 150 | 3.0%
2.2 | Collect and clean data | Software | Python, Excel |  |  | 0 | Software | Communication | 50 | 1.0%
2.3 | Upload and verify dataset | Human | Team | 6 | 30 | 180 | Human Resources | Total Budget | 4950 | 100%
3.1 | Design database ERD | Human | Database Developer | 12 | 35 | 420 | Human Resources
3.2 | Create database tables | Human | Database Developer | 10 | 35 | 350 | Human Resources
3.3 | Develop backend functions | Human | Backend Developer | 15 | 35 | 525 | Human Resources
4.1 | Collect training samples | Human | AI Engineer | 8 | 30 | 240 | Human Resources
4.2 | Train OCR/NLP model | Hardware | GPU Instance | 20 | 10 | 200 | Hardware/Cloud
4.3 | Evaluate model performance | Human | AI Engineer | 8 | 30 | 240 | Human Resources
5.1 | Design matching algorithm | Human | AI Engineer | 12 | 30 | 360 | Human Resources
5.2 | Implement algorithm | Human | Backend Developer | 12 | 35 | 420 | Human Resources
5.3 | Test matching accuracy | Human | Team | 6 | 30 | 180 | Human Resources
6.1 | Design dashboard UI | Human | UI Designer | 8 | 30 | 240 | Human Resources
6.2 | Develop frontend components | Human | Frontend Developer | 25 | 35 | 875 | Human Resources
6.3 | Integrate with backend | Human | Team | 10 | 30 | 300 | Human Resources
7.1 | Integrate all modules | Human | Full Stack Developer | 15 | 35 | 525 | Human Resources
7.2 | Run system-level testing | Human | Team | 8 | 30 | 240 | Human Resources
8.1 | Perform functional testing | Human | QA Engineer | 10 | 30 | 300 | Human Resources
8.2 | Conduct user acceptance test | Human | Team | 6 | 30 | 180 | Human Resources
9.1 | Deploy system to production | Human | DevOps | 8 | 20 | 160 | Human Resources
9.2 | Prepare user documentation | Human | Technical Writer | 6 | 20 | 120 | Human Resources
10.1 | Compile final report | Human | Project Lead | 12 | 30 | 360 | Human Resources
10.2 | Prepare presentation | Human | Project Lead | 4 | 30 | 120 | Human Resources
Total |  |  |  | 260 |  | 4950