## Week 03
Task | Duration | Owner | Status | Start date | End date | Dependencies | Estimated Cost (RM) | Milestone | Deliverable | Notes
Project Initiantion & Requirement Gathering | 5 | Muhammad Farouk | In progress | 2025-10-06 | 2025-11-03 | - | 1240 | ✅
Data Collection & Sourcing | 7 | Muhammad Farouk, Tee Kai En | In progress | 2025-10-13 | 2025-11-24 | 1 | 420
Backend & Database Development | 10 | Muhammad Aiman | Not started | 2025-11-24 | 2026-01-26 | 2 | 1295
AI Model Development (OCR & NLP) | 10 | Tee Kai En | Not started | 2025-11-24 | 2026-01-26 | 3 | 1080
AI Model Development (Matching Algorithm) | 8 | Tee Kai En, Muhammad Aiman | Not started | 2025-12-15 | 2026-02-02 | 4 | 1050
Frontend & Dashboard Development | 12 | Muhammad Aiman, Muhammad Farouk | Not started | 2025-11-17 | 2026-02-02 | 5 | 1505
System Integration | 7 | Muhammad Aiman | Not started | 2026-02-02 | 2026-02-09 | 6 | 805
Testing & Validation | 8 | Tee Kai En | Not started | 2026-02-09 | 2026-02-16 | 7 | 480
Deployment & Documentation | 1 | Tee Kai En | Not started | 2026-02-12 | 2026-02-19 | 8 | 280
Final Report & Presentation | 1 | Muhammad Farouk | Not started | 2026-02-12 | 2026-02-19 | 9 | 480
TOTAL | [6 empty] | 4950