## PDM_Table_WeekXX
Activity | Duration (days) | Predecessor | ES | EF | LS | LF | Slack
A | 5 | --- | 0 | 5 | 0 | 5 | 0
B | 7 | A | 5 | 12 | 5 | 12 | 0
C | 8 | B | 12 | 20 | 14 | 22 | 2
D | 10 | B | 12 | 22 | 12 | 22 | 0
E | 12 | C, D | 22 | 34 | 22 | 34 | 0
F | 10 | E | 34 | 44 | 34 | 44 | 0
G | 12 | E | 34 | 46 | 34 | 46 | 0
H | 5 | F, G | 46 | 51 | 46 | 51 | 0
I | 4 | H | 51 | 55 | 51 | 55 | 0

## Crashing_Analysis
Activity | Original Duration (days) | Crashed Duration (days) | Time Saved (days) | Additional Cost (RM) | Impact / Remarks
E | 12 | 10 | 2 | 200 | Extra GPU hours, additional developer support
G | 12 | 10 | 2 | 300 | Additional frontend developer, overtime work
Total Time Saved (days) |  |  | 4
Total Additional Cost (RM) |  |  |  | 500
Recalculated Schedule After Crashing:
• New duration of E: 10 days
• New duration of G: 10 days
• New project duration: 51 days (reduced by 4 days)
• New Critical Path: A → B → D → E → G → H → I
Crashing Results:
• New project duration: 51 days
• Critical path unchanged
• Effective? Yes – reduced timeline by 4 days but increased cost by RM500.
Trade-off between time and budget.